## Feuille 1
Request still pending | area | urgency | Status | Comment
Remove empty lines in all reports exported to excel - To apply formulas easily | Report | high | Done and working properly
Add boxes on transactions exported to excel - To prepare our documents accordingly | delivery | high | Done and working properly
Ability to upload and export to excel master category - Still not ready, can't upload, can't export to excel | master | medium | Done and working properly
Ability to upload and export to excel master colors - Still not ready, can't upload, can't export to excel | master | medium | Done and working properly
Report to summarize all sales orders in detail (per customer per style, full details) - for analysis/forecasts) | wholesale | medium | not started
Report to summarize all PO orders (same) - for analysis/forecasts | production | medium | not started
Report to summarize all purchasing orders - for analysis | purchasing | medium | not started
Report to summarize all sales wholesale (=already shipped)/include them in normal sales report | sales | very high | Done and working properly
Stock available - To be able to offer to our customers stock that is not already taken (details already given to team) | report | very high | Done and working properly
Add a way to upload prices in Euros different from corpo for SYA/specific requests - To have a more flexible possibility of uploading order with different prices than usual | sales order | high | Done and working properly
Ability to export masterlist with cost prices and all available info - For analysis, check of cost price and so on | master | high | Done and working properly
Dashboard for wholesale to link SO and Transaction numbers with amounts/amount not packed etc. (=export follow up) - To track down which transaction belong to what Sales order and double checking with the company in charge of export | report | high | Done and working properly
Add transactions in wholesale not yet shipped (=posted) to stock on hand/all stock reports - To track items fast and move from an order to another in case of payment issues | report | high | Done and working properly
show the Note when we print invoice : sales order and wholesale ( example : re-order, bulk ,sponsoring etc ) | acc and wholesale | high | Done and working properly | ok
stock card in shop and HO ( warehouse ) need soon - To check history in location | report | high | Done and working properly | only need check ready to use
Include in packing list report name of export client - So far we can't find export client easily and order numbers are not the same as the ones in the system | report | high | Done and working properly | no, still don't see it
in shop ,when we search stock ,by type 3 letters ( sgl.mby.ags,etc ) the result still show all item with all code and print ,in shop need fasilities " start with " to get result only what we search. | report | medium | Done and working properly
in shop, number of transaction ( number in cashier ) always starting no.00001 per day. ( for example : 1201-0419-010001 ) =1201 : name/no.station computer , 0419 : month and year ,01 : date(day) 0001 : cont.number. so if in one day there is 15 bill /receipt. the number will show : 010001 untill 010015. | shop cashier | low | not started
Ability to input / make manual number in wholesale ,to make same number in sales order and whole sale.(example : number sales order : SOR/93/0419/00001 , in whole sale number : TCA/93/0419/00001 | report | high | Done and working properly
Fix all bugs in reports (double entries and so on...)- Almost all of them have problems | report | very high | Done and working properly
Return from Outlet tidak bisa diposting karena qty di blok | form | high | Done and working properly
Penambahan "Class" di export master wholesale |  |  | Done and working properly
Penambahan grouping di print out wholesales summary |  |  | Done and working properly
penambahan nomer box di transfer konsigment |  |  | Done and working properly
Closing system baru dan lama setelah di kompare ditemukan selisih |  |  | Done and working properly
Stock Adjusment toko diminta tambahkan filter percatagori |  |  | Done and working properly
Gudang zalora dibuat gudang werehuuse baru |  |  | not started
penambahan multi price dan cost untuk export |  |  | Done and working properly
Semua report stock yang tidak ada qty di sizenya supaya kosong, jangan munculin nilai nol |  |  | Done and working properly
penjualan staff masukin ke cash person |  |  | Done and working properly
Stock available tambah di export transacton |  |  | Done and working properly
di sales register tambah payment type sales toko |  |  | Done and working properly
Link Account master item |  |  | Done and working properly
Find di return konsigment terlalu lama |  |  | Done and working properly
Reminder yang lama" supaya di hide |  |  | Done and working properly
Report sales summary per toko per date |  |  | Done and working properly
Surfretail Big Sales aktifkan update sales |  |  | - | sistem diubah menjadi offline
Buat report yang barcodenya tidak terbaca saat adjusment dan so |  |  | Done and working properly
user log diaktifkan di office |  |  | Done and working properly | Masih proses checked
Stock yang di toko supaya hanya data toko saja yang muncul, jangan munculin stock WH seperti sample, rijek, dll |  |  | Mitra working on it
ubah form payment diprogram big sales |  |  | -
sales register di tambahkan bank machine |  |  | Done and working properly
closing report dan summary sales diubah menjadi per user |  |  | Done and working properly
tambahkan alamat customer di print out whole sales dan sales order |  |  | Done and working properly | di print out sales order belum
tambahkan filter hide discountinued di product list |  |  | Done and working properly
Export Master di transfer to outlet ditambahkan season |  |  | Done and working properly
penambahan dashboard status pengiriman export |  |  | Done and working properly
di stock less minta ditambahkan direct langsung ke stock adjustment |  |  | Done and working properly
penginputan item di sales invoice diminta bsa 1 code dengan harga yg berbeda di pisahkan |  |  | not started
staff group msh belum sinkron dengan master staff |  |  | Done and working properly
return yg void di toko masih muncul direminder return system ho |  |  | Done and working properly
cost usd dan eur hilang di master product list |  |  | Done and working properly
Filter color/print di set discount menampilkan data double dan pada kolom color/print data yg tampil diubah menjadi nama color |  |  | Done and working properly
Return lended item yg sudah di save hilang saat di cari di find dan hasil cetak print blank |  |  | Done and working properly
What in stock dan stock card masih selisih ( perlu di lakukan pengecekan secara berkala) |  |  | Mitra working on it
Return from outlet tiba" posting sendiri dan user yg di gunakan itu user toko bukan staff office atau gudang |  |  | Done and working properly
Return di toko seminyak dan nusadua tidak muncul di reminder ho |  |  | Done and working properly
Format report summary sales berubah info dri bu agnes di toko lembongan |  |  | Done and working properly
Ada masalah di transaksi penjualan tgl 6 juni di toko lembongan |  |  | Done and working properly
Program kasir di sunset ngeprint transaksi makin hari,semakin lama |  |  | Done and working properly
Beda antara invoice di system vs saat akan di print |  |  | Done and working properly
Export stock menampilkan color berupa angka |  |  | Done and working properly
Error transaksi pada system lembongan |  |  | Done and working properly
Request import penjualan dari toko bigsale sunset ke system ho |  |  | Done and working properly
Muncul error duplicate no transaksi di system bigsale sunset tgl 5 juni 2019 |  |  | Done and working properly
Kolom color di transaksi muncul angka saat buat baru |  |  | Done and working properly
FOC Report diubah pengelompokannya menjadi per customer |  |  | Done and working properly
Ditoko tidak bisa Sync data master |  |  | Done and working properly
Di stock take system surfretail ditambahkan filter category |  |  | Done and working properly
Data sales summary bigsale sunset blm muncul |  |  | Done and working properly
tambahkan cashperson report di system |  |  | Done and working properly
tgl yg di tampilkan di stock card itu agar sales date di sales invoice yg di munculkan |  |  | Done and working properly
big sale sunset masuk ke sales consigment saat cek di sales invoice list |  |  | Done and working properly
masalah pada import data di receiving ( surfretail ) |  |  | Done and working properly
Hide toko online dan export di system surfretail |  |  | Done and working properly
report return lending summary no transaksi dan datenya tidak muncul |  |  | Done and working properly
report lending summary datanya tidak muncul |  |  | Done and working properly
penambahan fitur auto posting, auto box, input shipped di wholesale |  |  | Done and working properly
penambahan fitur seperti whole pada transfer to outlet |  |  | Done and working properly
di export status utk no invoice ubah menjadi no cargo dan tgl invoice di ubah menjadi tgl shipped |  |  | Done and working properly
di export transaksi wholesale ditambahkan tgl shipped dan no cargo |  |  | Done and working properly
Saat Print payment di toko yazz agak lambat |  |  | Done and working properly
masalah di wholesale yg jika qty pada sales order di ubah maka qty wholesale yg sudah di save jga ikut berubah |  |  | Done and working properly
penambahan fitur refresh di penarikan sales order tanpa menghilangkan qty scan di wholesale |  |  | Done and working properly
Di wholesale di tambahkan discount global |  |  | Mitra working on it
ada beberapa item yg blm isi color/printnya |  |  | Mitra working on it
pengelompokan sesuai tgl transaksi di sales summary masih salah |  |  | not started
Di cashperson di tambahkan discount global |  |  | not started
Tambahkan kolom disc dan subtotal di export master wholesale |  |  | Mitra working on it
Tambahkan toko consigment agar muncul juga di backorder |  |  | Mitra working on it
Tambah kolom disc dan sub total di cash person report ( Request Pak Tono ) |  |  | not started
Request dari pak Tono, di set discount ditambahkan colom sub catagori |  |  | Mitra working on it
Tambahkan warning jika item yg di scan tidak ada di no wholesale pada return wholesale |  |  | not started
Request report yang menampilkan detail barang transfer yg terkirim tapi belum di terima outlet |  |  | not started
Note on A6: Sum of all sales order with full details -Alexis Alfroy
Note on A7: Sum of all purchase orders -Alexis Alfroy
Note on A8: sum of all purchases -Alexis Alfroy
Note on A10: Different options to calculate the available stock: With production Without production With some shops/without some shops. Calculation is basically: If with production: Sum of production orders not finished + stock chosen shops + stock gudang - (Sales order - transaction attached to that SO) Example: if product X got 10 pcs in gudang 15 pcs in other shops 5 pcs in production not arrived yet 2 pcs in sales order but only 1 pcs already packed Stock available = 5+ 10 + 15 - (2-1) = 29 pcs available -Alexis Alfroy

## Feuille 2
- | Mitra done. Please confirm.
very high | not started
high | Mitra working on it
medium | 1st version done
low | Done and working properly
- | -